

Performance in initiating research Q1 2019-20

|  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **REC reference number** | **IRAS number** | **Name of study** | **Date Site Invited** | **Site Selected** | **HRA Approval** | **Site Confirmed by Sponsor** | **Non Confirmation Status** | **Site Ready to Start** | **First Patient Recruited** | **Reasons for delay** |
| 17/EM/0212 | 222015 | **StOIC**  An observational study of diagnostic criteria, clinical features and management of opioid induced constipation (OIC) in patients with cancer pain | 1 December 2017 | 21 March 2018 | 31 January 2018 | 19 March 2018 | N/A | 16 April 2018 | 17 April 2018 | N/A |
| 18/SC/0031 | 238243 | **Prosec 3**  A multi-centre evaluation of excessive saliva management in patients with Motor Neurone Disease | 14 September 2018 | 14 September 2018 | 21 January 2019 | 31 January 2019 | N/A | 06 February 2019 | N/A | N/A |



Performance in initiating research Q1 2019-20

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **REC reference number** | **IRAS number** | **Name of study** | **Recruitment target** | **Date agreed to recruit target by** | **Recruitment by agreed date** | **Total recruitment** | **Closed to Recruitment date** | **Reason for closure** |
| |  | | --- | | 16/LO/0631 | | |  | | --- | | 198753 | | **Alcohol Study**  An observational study investigating the prevalence and impact of alcohol-related problems in cancer patients and their non-professional caregivers | 50 | 30 March 2018 | 162 | 182 | 5 September 2018 | Recruitment completed |